## Sheet2
Development Plan | [5 empty] | Status
Tasks | Start | End | Resource | Days | Percentage
Sprint 1 | 09/25 | 10/08 | Narasimha, Rakesh | 10 | 5% | InProgress
220883_CR_BusinessResiliency_Bin Status Report EBS City Of Industry | 09/25 | 09/25 | Narasimha | 0.5 | 100% | Completed
220883_CR_BusinessResiliency_Bin Status Report EBS Beloit | 09/28 | 09/28 | Narasimha | 0.25 | 100% | Completed
220883_CR_BusinessResiliency_Raw Material Inventory Report EBS City Of Industry | 09/28 | 09/28 | Narasimha | 0.25 | 100% | Completed
220883_CR_BusinessResiliency_Raw Material Inventory Report EBS Beloit | 09/28 | 09/28 | Narasimha | 0.25 | 100% | Completed
220883_CR_BusinessResiliency_Raw Material Inventory Report EBS McDonough | 09/29 | 09/29 | Narasimha | 0.25 | 100% | Completed
220883_CR_BusinessResiliency_Customer Product Order History EBS City Of Industry | 09/29 | 09/29 | Narasimha | 0.25 | 100% | Completed
220883_CR_BusinessResiliency_Customer Product Order History EBS Beloit | 09/29 | 09/29 | Narasimha | 0.25 | 100% | Completed
220883_CR_BusinessResiliency_Customer Product Order History EBS McDonough | 09/29 | 09/29 | Narasimha | 0.25 | 100% | Completed
220883_CR_BusinessResiliency_Purchase Order History EBS Garland | 09/30 | 09/30 | Narasimha | 0.25 | 100% | Completed
220883_CR_BusinessResiliency_Purchase Order History EBS Martinsburg | 09/30 | 09/30 | Narasimha | 0.25 | 100% | Completed
220883_CR_BusinessResiliency_Purchase Order History EBS City of Industry | 09/30 | 09/30 | Narasimha | 0.25 | 100% | Completed
220883_CR_BusinessResiliency_Purchase Order History EBS Beloit | 09/30 | 09/30 | Narasimha | 0.25 | 100% | Completed
220883_CR_BusinessResiliency_Purchase Order History EBS McDonough | 09/30 | 09/30 | Narasimha | 0.25 | 100% | Completed
220883_CR_BusinessResiliency_Basic Customer Master Data EBS Garland | 10/01 | 10/01 | Narasimha | 0.25 | 100% | Completed
220883_CR_BusinessResiliency_Basic Customer Master Data EBS Martinsburg | 10/01 | 10/01 | Narasimha | 0.25 | 100% | Completed
220883_CR_BusinessResiliency_Basic Customer Master Data EBS City of Industry | 10/01 | 10/01 | Narasimha | 0.25 | 100% | Completed
220883_CR_BusinessResiliency_Basic Customer Master Data EBS Beloit | 10/01 | 10/01 | Narasimha | 0.25 | 100% | Completed
220883_CR_BusinessResiliency_Basic Customer Master Data EBS McDonough | 10/01 | 10/01 | Narasimha | 0.25 | 100% | Completed
Sprint 1 Validation Session | 10/05 | 10/05 | Narasimha | 1 | 0% | Yet to start
220883_CR_BusinessResiliency_Design_System Integartion Testing | 10/06 | 10/06 | Narasimha | 1 | 70% | InProgress
Documentation update (SDD, Runbook) | 10/16 | 10/18 | Narasimha | 3 | 0% | Yet to start
Buiness Validation Support | 10/12 | 10/13 | Narasimha, Rakesh | 1 | 0% | Yet to start
Deployment and Hypercare Support | 10/14 | 10/16 | Narasimha | 3 | 0% | Yet to start